## Task Priority Box
| Urgent | Not urgent
Important | - Review progress in last week - Plan for new week + handle management task | - Make presentation for Screen manager - Present content to team - Detailed plan for intern (4 remain weeks) - Finish refactory code for handling BACK events - Finish resignation form
Not important | - Review code + make improvement list for intern
Note on B5: Author: DO IT NOW
Note on C5: Author: SCHEDULE TIME TO DO
Note on B6: Author: DELEGATE IT TO OTHER
Note on C6: Author: DROP OR ELEMINATE IT

## Apr2017
Current time |  | 2017-04-07 08:43
Time Slot | 2017-04-03 |  | 2017-04-04 |  | 2017-04-05 |  | 2017-04-06 | 2017-04-07
8 h |  |  |  |  | - Make TODO list | Finished
| - Make personal daily plan | Finish | - Hand-over intern program to Thanh - Review code for Corepart - Share Screen manager document to team | Finish | - Finish resolving conflict for refactory Model | Doing
9 h | - Review progress in last week | Finish | - Review refactory part of Corepart | Finish
| - Team meeting to review progress and decide next action | Finish | - Meeting in Qsoft | Finish
10 h | - Finish refactory code to handle BACK | Doing | - Meeting in Qsoft | Finish | Make detailed plan for remain intern program | Not started
|  |  | - Meeting in Qsoft | Finish | Tech discussion with Team + Overall flow + Remain items: port communication, Module sepration + HARD keys handling | Finished
11 h | - Finish documentation for inter-component communication + BACK handling - Send document to team for quick check | Doing | Update Design document | Finish
Buffer
12 h
13 h | - Make weekly plan for intern | Doing | - Revise Design document + Change content flow (details explanation for whole Model moved into last) + Add IN/OUT data flow for Model part + Add explanation for handling BACK events (why need, some approaches and current results) | Finish | Finish paper work before resignation | Doing
- Review progress
14 h | - Review Model team result - Make solution for tech issue - Share techniques for modeling | Doing |  |  | Review all spec amd make improvement list in details | Finish
15 h |  |  |  |  | Update design documents | Not started
16 h | - Present content to team | Finish |  |  | Train Tung and Phuc about Port communication in more details | Not started
17 h
18 h
19 h
Summary | - Time for unplanned longer than expectation => impacted on planned task - Should have buffer for extra-task: talk with intern, paper work and so on |  | - Had 2h OT due to following reasons + Debugging code and waiting for Rhapsody building code + Need to join IDR meeting with team |  | - Spent too much time to resolve floict of Rhapsody
Not started
Doing
Finish
Delayed
Postponse
Sooner than plan

## March2017
Current time |  | 2017-04-07 08:43
Time Slot | 2017-03-27 |  | 2017-03-28 |  | 2017-03-29 |  | 2017-03-30 |  | 2017-03-31
8 h | + Review team progress + Make personal daily plan | Finish | + Review team progress + Make personal daily plan | Finish | + Review team progress + Make personal daily plan + Push libHMI.a to master | Finish | + Make WR report + Review team progress (hand-over focused) | Finish | + Review team progress (hand-over focused) | Doing
9 h | + Team meeting + Make weekly plan for intern | Finish | - Fix bugs of Overlay related to pop-up | Finish | + Revise Model Project and push to libHMI + Discuss with Qsoft Members about project issues | Finish | + Review team progress (hand-over focused) + Update intern progress + Push updated version for Model & libHMI repos | Finish | + Review intern results + Finish personal tax related document | Doing
10 h | + Do HOT fix for overlay management w/o optimization | Postponse |  |  | + Review intern result + Discuss with Qsoft Members about project issues | Doing | Make documentation + Re-outline content + Components inter-communication | Doing | - Relayout to show Event Bus Pattern | Not started
11 h | + Do HOT fix for overlay management w/o optimization | Finish |  |  | - Fix bug for Overlay / show Log + Review intern result Update documentation + Screen-related events handling ( + BACK) + OXF Thread and queuing | Finish | Make documentation + Re-outline content + Components inter-communication | Doing | Make documentation + Components inter-communication | Not started
|  |  | Make document index | Finish
12 h
13 h | + Fix BACK button | Postponse | Update documentation + Overview of Modeling part => Done + Definitions: Auto-hide => Not done + Approaches in designing overlay mangement => Not done (just have idea) | Doing | + Weekly report | Delayed | Make documentation + Re-outline content + Components inter-communication | Doing | Make documentation | Not started
14 h |  |  |  |  | Make detailed requirement for intern | Not started | Make documentation + Re-outline content + Components inter-communication | Doing | Make documentation + Components inter-communication | Not started
| + Fix BACK button | Postponse
15 h | + Fix BACK button + Make summary documentation for BUG | Postponse |  |  | Update documentation + Screen-related events handling ( + BACK) + OXF Thread and queuing | Doing | Make documentation + Re-outline content + Components inter-communication | Doing | Make documentation + Components inter-communication | Not started
16 h | + Share Overlay know-how | Finish |  |  |  |  | Share Components inter-communication | Not started | Share Components inter-communication | Not started
|  |  | + Share Overlay know-how | Finish
17 h | + Share Overlay know-how | Finish
|  |  | + Review intern result | Not started
18 h | + Share Overlay know-how | Finish
| + Share Overlay know-how | Finish
19 h | + Review intern result | Not started
Summary | - Can not finish fixing bugs for BACK button - Have 2h OT to finish jobs exclude fixing bugs of BACK buttons |  | - Not enough time to review intern result - Design documents shoule be changed into better and easier to understand way - Change plan to make documentation - Time to fix bug for overlay shorter than plan - Need more time to make outline documents before making details |  |  |  | - Not finish goal to share know-how + making documentation + Unplanned task: refactory code + talk with intern longer than plan
Not started
Doing
Finish
Delayed
Postponse
Note on C4: Author: due to explaing to intern longer than expectation
Note on B5: Author: Postpone fore team meeting
Note on C9: Author: Postpone for fixing bugs of overlay